## Sheet1
Component | Description | Status | Effort (Days) | Owner | Start Date | Completion Date | Comments
Explore the javascript componet for drawing | Figure out the opensource javascript modules that give the drawing. | New | 2
Write javascript code for frame size in java script | Refer method drawDecideFrameSize | New | 1
Write javascript code for filling the polycon | Refer methods drawDrawOverState, drawCheckState, drawFoundState | New | 1
Write javascript to validate the inputs | Error handling of the input values | New | 1
Add functionality for next iteration and pervioud iteration |  | New | 1
Add functionality for back button |  | New | 1
Support the algorithm for multiple polygons |  | New | 1
Run test cases that written against java script |  | New | 1
Run the metrics on the java script and compare them with metrics from java code. |  | New | 1
Fix the issues found in java code | Fix the issues in javascript | New | 1